## RACI Matrix
# | Phase | Node ID | Step Description | Type | Company Counsel | Issuer (Mgmt) | Underwriters | UW Counsel | Accountants | Reserve Engineer | Tax Counsel | SEC/FINRA/Exch
VDR Readiness
1 | VDR Readiness | Milestone_IPOTrigger | TRIGGER: Sponsor decides to pursue IPO | MILESTONE
2 | VDR Readiness | Issuer_EstablishVDR | Issuer: Establish & populate VDR folders (Financials, Reserves, Ops, Legal, Governance, Risks, Tax) | ACTION | C | R |  |  | I
3 | VDR Readiness | Issuer_RunChecklistComparison | Issuer: Run VDR index against S-1 checklist | ACTION | C | R |  |  | I
4 | VDR Readiness | Issuer_FlagVDRGaps | Issuer: Flag missing or incomplete VDR items | ACTION | C | R |  |  | I
5 | VDR Readiness | Issuer_ConfirmPhysicalComplete | Issuer: Confirm physical completeness of VDR folders | ACTION | C | R |  |  | I
6 | VDR Readiness | Decision_VDRReady | VDR ready for S-1 drafting? | DECISION
Section Assignment & Kickoff
7 | Section Assignment & Kickoff | Issuer_AssignSectionOwners | Issuer: Assign S-1 section owners (Counsel→1/1A/3; Acctg→7/8; Bankers→UoP/Cap/Dil; Ops→reserves) | ACTION | C | R | I | I | I
8 | Section Assignment & Kickoff | Issuer_HoldOrgMeeting | Issuer: Hold organizational meeting (style guide, drafting timeline, gun-jumping rules, comps) | ACTION | C | R | I | I | I | I | I
Direct Input Production
9 | Direct Input Production | ResEng_PrepareReserveReport | Reserve Engineer: Engage reserve engineer for SEC reserve report from VDR>Reserves per Reg S-X 4-10(a) | ACTION | I | A |  |  | I | R
10 | Direct Input Production | Acct_CommenceAudit | Accountants: Commence audited FS from VDR>Financials (3yr non-EGC / 2yr EGC; pro forma) | ACTION | I | A |  |  | R
11 | Direct Input Production | CompCounsel_ReviewMatlContracts | Company Counsel: Review material contracts from VDR>Legal | ACTION | R | A
12 | Direct Input Production | CompCounsel_ReviewRelPartyTxn | Company Counsel: Review related-party transactions (current + 3 prior yrs) | ACTION | R | A
13 | Direct Input Production | CompCounsel_ReviewLitigation | Company Counsel: Review litigation, environmental & regulatory from VDR>Risks | ACTION | R | A
14 | Direct Input Production | CompCounsel_FlagDDGaps | Company Counsel: Flag DD gaps; counsel reviews findings | ACTION | R | A |  | I
15 | Direct Input Production | Issuer_CompileOpsData | Issuer: Compile acreage, drilling locations, infrastructure from VDR>Ops | ACTION | C | R |  |  | I | I
Phase 2A: S-1 Exhibit Document Drafting
16 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_ExtractGovTerms | Company Counsel: Extract governance terms from VDR>Governance | ACTION | R | A
17 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_DraftUnitholderRights | Company Counsel: Draft unitholder rights & GP powers provisions | ACTION | R | A
18 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_DraftIDRSubord | Company Counsel: Draft IDR tier structure & subordination period mechanics | ACTION | R | A
19 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_DraftFiduciary | Company Counsel: Draft fiduciary duty modifications & conflicts provisions | ACTION | R | A
20 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_ReviewLPADraft | Company Counsel: Review & negotiate complete LPA draft | ACTION | R | A | I | C
21 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_DraftContribAgt | Company Counsel: Draft Contribution Agreement from VDR>Governance (sponsor assets → MLP) | ACTION | R | A |  |  |  |  | I
22 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_DraftOmnibusAgt | Company Counsel: Draft Omnibus Agreement from VDR>Legal (indemnification, non-compete, ROFO) | ACTION | R | A | I | C |  |  | I
23 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_DraftServicesAgt | Company Counsel: Draft Services Agreement from VDR>Governance | ACTION | R | A |  |  |  |  | I
24 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_DraftRegRightsAgt | Company Counsel: Draft Registration Rights Agreement from VDR>Governance | ACTION | R | A |  |  |  |  | I
25 | Phase 2A: S-1 Exhibit Document Drafting | CompCounsel_DraftLTIP | Company Counsel: Draft LTIP from VDR>Governance | ACTION | R | A |  |  |  |  | I
26 | Phase 2A: S-1 Exhibit Document Drafting | TaxCounsel_ObtainTaxOpinion | Tax Counsel: Obtain tax opinion from VDR>Tax (qualifying income, pass-through, disguised sale rules) | ACTION | C | A |  |  |  |  | R
Phase 2B: S-1 Prospectus Drafting
27 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_PullOpsData | Company Counsel: Pull acreage, drilling & reserve data from VDR>Ops | ACTION | R | A |  |  |  | I
28 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftCompStrengths | Company Counsel: Draft competitive strengths narrative | ACTION | R | A | I
29 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftBizStrategy | Company Counsel: Draft business strategy & midstream advantage sections | ACTION | R | A | I
30 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftReserveDisc | Company Counsel: Draft reserve disclosure per Reg S-K Subpart 1200 | ACTION | R | A |  |  |  | C
31 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_VerifyReserveConsist | Company Counsel: Verify Item 1 consistency with reserve engineer report | ACTION | R | A |  |  |  | C
32 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_AssistItem1 | Company Counsel: Assist Item 1 narrative (tone, reserve report consistency) | ACTION | R | A |  |  |  | C
33 | Phase 2B: S-1 Prospectus Drafting | Issuer_AnalyzeProdPriceCost | Issuer: Analyze production, price & cost trends from VDR>Financials | ACTION | C | R |  |  | I
34 | Phase 2B: S-1 Prospectus Drafting | Issuer_DraftMDANarrative | Issuer: Draft MD&A narrative (liquidity, capital resources, known trends) | ACTION | C | R |  |  | C
35 | Phase 2B: S-1 Prospectus Drafting | Issuer_MgmtVerifyMDA | Issuer: CFO/management verify MD&A numbers & business context | ACTION | C | R |  |  | C
36 | Phase 2B: S-1 Prospectus Drafting | Issuer_GenerateMDATables | Issuer: Generate MD&A sensitivity tables & pro forma schedules | ACTION | C | R |  |  | C
37 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftCommodityRisks | Company Counsel: Draft commodity price & reserve estimation risk factors | ACTION | R | A |  |  |  | C
38 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftRegEnvRisks | Company Counsel: Draft regulatory & environmental risk factors | ACTION | R | A
39 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftMLPRisks | Company Counsel: Draft MLP-specific risks (conflicts, IDR dilution, limited voting rights) | ACTION | R | A
40 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftTaxRisks | Company Counsel: Draft unitholder tax risks (UBTI, K-1 complexity, state filing obligations) | ACTION | R | A |  |  |  |  | C
41 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_CrossCheckSECTrends | Company Counsel: Cross-check risk factors against SEC comment letter trends for E&P MLPs | ACTION | R | A
42 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_ExpandRiskFactors | Company Counsel: Expand Risk Factors with mitigants & detailed disclosure language | ACTION | R | A
43 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftLegalProc | Company Counsel: Draft Item 3 Legal Proceedings from VDR>Risks | ACTION | R | A
44 | Phase 2B: S-1 Prospectus Drafting | Acct_PrepareFS | Accountants: Prepare Item 8 FS & Notes (PCAOB) from VDR>Financials | ACTION | I | A |  |  | R
45 | Phase 2B: S-1 Prospectus Drafting | Issuer_ComputeUoP | Issuer: Compute Use of Proceeds from offering terms | ACTION | C | R | C
46 | Phase 2B: S-1 Prospectus Drafting | Issuer_BuildCapDilTables | Issuer: Build Capitalization & Dilution tables | ACTION | C | R | C
47 | Phase 2B: S-1 Prospectus Drafting | Issuer_BankersSetTerms | Issuer: Bankers/counsel set offering terms & verify tables | ACTION | C | R | C | C
48 | Phase 2B: S-1 Prospectus Drafting | Acct_PrepareSelFinData | Accountants: Prepare Selected Financial Data from VDR>Financials | ACTION | I | A |  |  | R
49 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_ExtractLPADistTerms | Company Counsel: Extract MQD & IDR terms from LPA | ACTION | R | A | I
50 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftSubordMechanics | Company Counsel: Draft subordination period mechanics narrative | ACTION | R | A
51 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftIDRSplitDisc | Company Counsel: Draft IDR split schedule & distribution waterfall | ACTION | R | A | I
52 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_GenerateCashDistNarr | Company Counsel: Generate Cash Distribution narrative with IDR tier examples | ACTION | R | A | I
53 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DistillEquityStory | Company Counsel: Distill equity story & competitive strengths for Summary | ACTION | R | A | I
54 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_CompileFinSummary | Company Counsel: Compile summary financial data & offering terms | ACTION | R | A | I |  | I
55 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftBoxSection | Company Counsel: Draft Box section (front-of-prospectus summary) | ACTION | R | A | I
56 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_AssistSummaryBox | Company Counsel: Assist Summary/Box (tone, trace claims to detailed sections) | ACTION | R | A | I
57 | Phase 2B: S-1 Prospectus Drafting | TaxCounsel_DraftPassThrough | Tax Counsel: Draft pass-through taxation & K-1 reporting sections | ACTION | C | A |  |  |  |  | R
58 | Phase 2B: S-1 Prospectus Drafting | TaxCounsel_DraftUBTIStateForeign | Tax Counsel: Draft UBTI, state filing & foreign investor withholding | ACTION | C | A |  |  |  |  | R
59 | Phase 2B: S-1 Prospectus Drafting | TaxCounsel_VerifyTaxAccuracy | Tax Counsel: Tax counsel verify technical accuracy of all tax sections | ACTION | C | A |  |  |  |  | R
60 | Phase 2B: S-1 Prospectus Drafting | TaxCounsel_AssistTaxConseq | Tax Counsel: Assist Tax Consequences (unitholder tax scenarios) | ACTION | C | A |  |  |  |  | R
61 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftUnitsDesc | Company Counsel: Draft Description of Common Units from LPA | ACTION | R | A
62 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftSellingUnitholders | Company Counsel: Draft Selling Unitholders section | ACTION | R | A
63 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_DraftUnderwriting | Company Counsel: Draft Underwriting section (w/ UW counsel input on negotiated terms) | ACTION | R | A | C | C
64 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_PreparePartII | Company Counsel: Prepare Part II (indemnification, unregistered sales, expenses) | ACTION | R | A
65 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_CompileMatlContracts | Company Counsel: Compile material contracts as exhibits from VDR>Legal | ACTION | R | A
66 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_ObtainExhibitConsents | Company Counsel: Obtain reserve engineer, auditor & nominee consents | ACTION | R | A |  |  | C | C
67 | Phase 2B: S-1 Prospectus Drafting | CompCounsel_IndexOrgDocs | Company Counsel: Index organizational documents & verify exhibit list completeness | ACTION | R | A
68 | Phase 2B: S-1 Prospectus Drafting | Decision_SectionsConsistent | Sections consistent with each other? | DECISION
Phase 2C: Internal Review Cycles
69 | Phase 2C: Internal Review Cycles | CompCounsel_Review1VDR | Company Counsel: First review: cross-check against VDR | ACTION | R | A |  |  | I
70 | Phase 2C: Internal Review Cycles | CompCounsel_Review2CrossRefs | Company Counsel: Second review: cross-refs, defined terms, financial ties (MD&A↔FS↔Summary↔Cap) | ACTION | R | A | I |  | I
71 | Phase 2C: Internal Review Cycles | CompCounsel_CheckDefinedTerms | Company Counsel: Cross-check defined terms consistency; flag mismatches | ACTION | R | A |  |  | I
72 | Phase 2C: Internal Review Cycles | CompCounsel_CheckNarrConsist | Company Counsel: Check narrative consistency across all sections | ACTION | R | A |  |  | I
73 | Phase 2C: Internal Review Cycles | CompCounsel_ReviewGunJumping | Company Counsel: Review for gun-jumping compliance (30-day bright-line test) | ACTION | R | A | I | I
74 | Phase 2C: Internal Review Cycles | CompCounsel_VerifyFLSSafeHarbor | Company Counsel: Verify forward-looking statement safe harbor language | ACTION | R | A
75 | Phase 2C: Internal Review Cycles | CompCounsel_Section11Review | Company Counsel: Full Section 11 liability review of registration statement | ACTION | R | A |  | I | I
76 | Phase 2C: Internal Review Cycles | Decision_ReviewResolved | All review comments resolved? | DECISION
77 | Phase 2C: Internal Review Cycles | Issuer_FinalSignOff | Issuer: Execute final internal sign-off on draft S-1 | ACTION | C | R | I | I | I
Phase 3: S-1 Filing Preparation
78 | Phase 3: S-1 Filing Preparation | CompCounsel_PrepareIndemAgt | Company Counsel: Prepare indemnification agreements (S-1 exhibit) | ACTION | R | A | I | C
79 | Phase 3: S-1 Filing Preparation | CompCounsel_ObtainCUSIP | Company Counsel: Obtain CUSIP number | ACTION | R | A
80 | Phase 3: S-1 Filing Preparation | CompCounsel_CollectSigPages | Company Counsel: Collect executed signature pages & powers of attorney | ACTION | R | A
81 | Phase 3: S-1 Filing Preparation | CompCounsel_ObtainCIKCCC | Company Counsel: Obtain CIK/CCC EDGAR codes | ACTION | R | A
82 | Phase 3: S-1 Filing Preparation | CompCounsel_CheckRegSK | Company Counsel: Check Reg S-K narrative disclosure requirements | ACTION | R | A
83 | Phase 3: S-1 Filing Preparation | CompCounsel_CheckRegSX | Company Counsel: Check Reg S-X financial statement requirements | ACTION | R | A |  |  | C
84 | Phase 3: S-1 Filing Preparation | CompCounsel_VerifySigExhibits | Company Counsel: Verify signatures, powers of attorney & exhibit list | ACTION | R | A
85 | Phase 3: S-1 Filing Preparation | CompCounsel_Edgarize | Company Counsel: Edgarize S-1 & exhibits; test EDGAR filing | ACTION | R | A | [5 empty] | I
86 | Phase 3: S-1 Filing Preparation | CompCounsel_PrepareRule134 | Company Counsel: Prepare Rule 134 press release | ACTION | R | A | I
87 | Phase 3: S-1 Filing Preparation | Decision_S1Ready | S-1 ready for submission? | DECISION
Filing with SEC, FINRA, and Exchange
88 | Filing with SEC, FINRA, and Exchange | CompCounsel_AssembleDRSPackage | Company Counsel: Assemble final S-1 + all exhibits into DRS package | ACTION | R | A |  |  | I |  |  | I
89 | Filing with SEC, FINRA, and Exchange | CompCounsel_VerifyExhibitsAttached | Company Counsel: Verify all exhibits & consents attached | ACTION | R | A
90 | Filing with SEC, FINRA, and Exchange | CompCounsel_CounselConfirmDRS | Company Counsel: Counsel confirms DRS completeness for submission | ACTION | R | A |  | I |  |  |  | I
91 | Filing with SEC, FINRA, and Exchange | Acct_ObtainAuditorConsent | Accountants: Obtain signed auditor's consent | ACTION | C | A |  |  | R
92 | Filing with SEC, FINRA, and Exchange | CompCounsel_SubmitDRS | Company Counsel: Submit confidential DRS via EDGAR | ACTION | R | A | I | I | I |  |  | I
93 | Filing with SEC, FINRA, and Exchange | UWCounsel_FileFINRA | UW Counsel: File with FINRA within 1 business day (Rule 5110) | ACTION | I | I | A | R |  |  |  | I
94 | Filing with SEC, FINRA, and Exchange | UWCounsel_SubmitExchange | UW Counsel: Submit S-1 to NYSE/Nasdaq for review | ACTION | I | I | A | R
95 | Filing with SEC, FINRA, and Exchange | Acct_ComfortLetterScope | Accountants: Discuss comfort letter scope (AS 6101); circle-up begins; auditors deliver initial draft | ACTION | C | A | I | C | R
SEC Review & Amendment Cycle
96 | SEC Review & Amendment Cycle | SEC_AssignExaminer | SEC: SEC assigns examiner team (Div of Corp Finance) | ACTION | I | I | [5 empty] | R
97 | SEC Review & Amendment Cycle | SEC_CommentLetterReceived | SEC: SEC comment letter received? (27-30 cal days) | DECISION
98 | SEC Review & Amendment Cycle | CompCounsel_CategorizeSECComments | Company Counsel: Categorize SEC comments by section (reserves, MD&A, risks, tax, other) | ACTION | R | A |  |  | I | C | C
99 | SEC Review & Amendment Cycle | CompCounsel_DraftResponseLetter | Company Counsel: Draft response letter addressing each comment | ACTION | R | A |  |  | C
100 | SEC Review & Amendment Cycle | CompCounsel_DraftS1AAmendments | Company Counsel: Draft proposed S-1/A amendments per responses | ACTION | R | A |  |  | C
101 | SEC Review & Amendment Cycle | CompCounsel_CounselMgmtReview | Company Counsel: Counsel & management review responses & amendments | ACTION | R | A |  | I
102 | SEC Review & Amendment Cycle | CompCounsel_FileAmendedDRS | Company Counsel: File amended DRS (S-1/A) via EDGAR | ACTION | R | A | I |  |  |  |  | I
103 | SEC Review & Amendment Cycle | SEC_FollowUpComments | SEC: SEC follow-up comments? (2-3 wks) | DECISION
104 | SEC Review & Amendment Cycle | SEC_AllCommentsCleared | All SEC comments cleared? | DECISION
105 | SEC Review & Amendment Cycle | CompCounsel_PublicFileConf | Company Counsel: Publicly file all prior confidential submissions (≥15 days before roadshow) | ACTION | R | A | C | C |  |  |  | I
106 | SEC Review & Amendment Cycle | UWCounsel_UpdateFINRA | UW Counsel: Update FINRA filing; pay additional fees | ACTION | I | I | A | R |  |  |  | I
107 | SEC Review & Amendment Cycle | SEC_FINRANoObjections | FINRA: No Objections or Unreasonable? | DECISION
108 | SEC Review & Amendment Cycle | UWCounsel_ObtainFINRALetter | UW Counsel: Obtain FINRA No Objections letter (15-25 bus. days) | ACTION | I | I | A | R |  |  |  | I
109 | SEC Review & Amendment Cycle | SEC_ExchangeApproved | Exchange listing approved? | DECISION
Phase 5: Pre-Effectiveness Filing Mechanics
110 | Phase 5: Pre-Effectiveness Filing Mechanics | CompCounsel_FileRedHerring | Company Counsel: File & print preliminary prospectus (red herring) | ACTION | R | A | I | I
111 | Phase 5: Pre-Effectiveness Filing Mechanics | UWCounsel_PrepareBlueSky | UW Counsel: Prepare preliminary blue sky memo | ACTION | I | I | A | R
112 | Phase 5: Pre-Effectiveness Filing Mechanics | CompCounsel_ReviewRoadshow | Company Counsel: Review roadshow for S-1 consistency & gun-jumping | ACTION | R | A | C | C
113 | Phase 5: Pre-Effectiveness Filing Mechanics | CompCounsel_IssueLaunchPR | Company Counsel: Issue Rule 134 launch press release | ACTION | R | A | I
114 | Phase 5: Pre-Effectiveness Filing Mechanics | CompCounsel_PrepareForm3s | Company Counsel: Prepare Form 3s (Sec 16 beneficial ownership) | ACTION | R | A
115 | Phase 5: Pre-Effectiveness Filing Mechanics | CompCounsel_PrepareForm8A | Company Counsel: Prepare Form 8-A (Exchange Act registration) | ACTION | R | A
116 | Phase 5: Pre-Effectiveness Filing Mechanics | CompCounsel_FinalizeListingApp | Company Counsel: Finalize listing application; confirm exchange approval | ACTION | R | A |  | I
117 | Phase 5: Pre-Effectiveness Filing Mechanics | Decision_FSCurrent | FS current under 135-day staleness rule? | DECISION
118 | Phase 5: Pre-Effectiveness Filing Mechanics | Decision_PreEffConditions | All pre-effectiveness conditions met? (FINRA, exchange, FS, consents) | DECISION
Phase 6: Effectiveness
119 | Phase 6: Effectiveness | Issuer_BringDownDD | Issuer: Conduct bring-down DD call | ACTION | C | R | C | C | C
120 | Phase 6: Effectiveness | CompCounsel_RequestAccel | Company Counsel: Deliver to SEC request for acceleration (Rule 461; 2 bus. days prior) | ACTION | R | A | C |  |  |  |  | I
121 | Phase 6: Effectiveness | UW_JoinAccelRequest | Underwriters: Deliver to SEC letter joining acceleration request | ACTION | I | I | R | C |  |  |  | I
122 | Phase 6: Effectiveness | SEC_DeclaresEffective | SEC declares S-1 effective? | DECISION
123 | Phase 6: Effectiveness | Milestone_Effective | SEC DECLARES REGISTRATION STATEMENT EFFECTIVE — END — | MILESTONE

## Legend
RACI Definitions
R | Responsible — performs the work
A | Accountable — approves/owns the outcome; ultimate authority
C | Consulted — provides input before/during the work
I | Informed — notified of the outcome after completion
Role Color Key
#0072B2 | Company Counsel
#E69F00 | Issuer (Mgmt)
#56B4E9 | Underwriters
#009E73 | UW Counsel
#F0E442 | Accountants
#D55E00 | Reserve Engineer
#CC79A7 | Tax Counsel
#000000 | SEC/FINRA/Exch
Notes
1. | Decision and milestone nodes have no RACI assignments (process control points).
2. | Issuer (Management) is Accountable for most steps as the registrant with Section 11 liability.
3. | Underwriters are Accountable for UW Counsel steps as the engaging party.
4. | SEC/FINRA/Exchange steps have no separate Accountable — external regulatory actions.
5. | Where a role is both R and A, only R is shown (applies to all self-accountable roles, including Issuer and Underwriters steps).

## Summary
Role | R | A | C | I
Company Counsel | 75 | 0 | 23 | 11
Issuer (Mgmt) | 16 | 86 | 0 | 7
Underwriters | 1 | 5 | 8 | 23
UW Counsel | 5 | 0 | 10 | 11
Accountants | 5 | 0 | 8 | 19
Reserve Engineer | 1 | 0 | 6 | 3
Tax Counsel | 5 | 0 | 2 | 6
SEC/FINRA/Exch | 1 | 0 | 0 | 11
Total | 109 | 91 | 57 | 91